## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Group 1
Group Member: | David B |  | Progress Classes: | Ahead
Group Member: | Josh C |  |  | On-track |  | Number of task corresponds to weekly contribution**
Group Member: | David P |  |  | Behind
Group Member: | Jack L |  |  | Way Behind
Tutor: | Zainab & Ali
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | David B | Josh C | David P | Jack L
|  |  | Group Formed |  | Weekly Contribution | Emailed Tutor to form group and set up Github repo, Group Formed | MS Team Created, Group Formed | Group Formed | Group Formed
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes | Meeting 12/07/2023 - 6:30 - 7 pm | Meeting 12/07/2023 - 6:30 - 7 pm | Meeting 12/07/2023 - 6:30 - 7 pm | Meeting 12/07/2023 - 6:30 - 7 pm
|  |  | Initial team meeting 6.30-7pm 12/07/23 |  |  | Attended | Attended | Attended | Attended
|  | Progress | Ahead
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | David B | Josh C | David P | Jack L
|  | 1 | Choice of where to use linked list, vector & array |  | Weekly Contribution | 1, 2, 4, 7 | 1, 2, 3, 5, | 1,2, 6, 7 | 1, 3, 4
|  | 2 | Initial Design of ADTs (classes and potential methods) |  | Issues
|  | 3 | Main menu |  | Other Notes | Meeting 17/07/23 - 7:00 - 8:00pm | Meeting 17/07/23 - 7:00 - 8:00pm | Meeting 17/07/23 - 7:00 - 8:00pm | Meeting 17/07/23 - 7:00 - 8:00pm
|  | 4 | User Prompt (for gameplay), but no/minimal error checking |  |  | Attended | Attended | Attended | Attended
|  | 5 | Linked List implementation |  |  | Link list implemented, may need to tweek as we go
|  | 6 | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
|  | 7 | ADT implementation for storing information, game loop logic not required
Team meeting 7:00 - 8:00pm - 17/07/23
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | David B | Josh C | David P | Jack L
|  | 1 | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | 1, 2, 4 | 1, 2, 4 | 1, 2, 4 | 3
|  | 2 | Initialisation of data strctures for new game |  | Issues
|  | 3 | Write Tests Cases for common uses |  | Other Notes | Meeting 24/07/23 - 7:00 - 8:45pm | Meeting 24/07/23 - 7:00 - 8:45pm | Meeting 24/07/23 - 7:00 - 8:45pm | Meeting 24/07/23 - 7:00 - 8:45pm
|  | 4 | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic |  |  | Attended | Attended | Attended | Attended
|  |  | Team meeting 7:00 - 8:45pm - 24/07/23 |  |  | Meeting 25/07/23 - 7:30 - 8:00pm | Meeting 25/07/23 - 7:30 - 8:00pm | Meeting 25/07/23 - 7:30 - 8:00pm | Meeting 25/07/23 - 7:30 - 8:00pm
|  |  | Team meeting 7:30 - 8:00pm - 25/07/23 |  |  | Attended | Attended | Attended | Attended
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | David B | Josh C | David P | Jack L
|  | 1 | Fully complete implementation and error free |  | Weekly Contribution | 1, 2, 3, 5 | 1, 2, 3, 5 | 1, 2, 3, 5 | 1, 2, 4, 5
|  | 2 | Full error checking of user prompt |  | Issues
|  | 3 | Automated placement of tiles at end of round, but no scoring |  | Other Notes | Meeting 31/07/23 - 7:00 - 7:50pm | Meeting 31/07/23 - 7:00 - 7:50pm | Meeting 31/07/23 - 7:00 - 7:50pm | Meeting 31/07/23 - 7:00 - 7:50pm
|  | 4 | Final Tests |  |  | Attended | Attended | Attended | Attended
|  | 5 | Group Report Written
|  |  | Team meeting 7:00 - 7:50pm 31/07/23 |  |  | Meeting 6/08/23 - 4:30 - 7:30pm | Meeting 6/08/23 - 4:30 - 7:30pm | Meeting 6/08/23 - 4:30 - 7:30pm | Meeting 6/08/23 - 4:30 - 7:30pm
|  |  | Team meeting 4:30 - 7:30pm 6/08/23 |  |  | Attended | Attended | Attended | Attended
|  | Progress | On-track